## Sheet1
Project Name: Beginner Japanese Course Timeline Version Number: 1.000 (Master) | [10 empty] | Date:02/07/2020
| Allocated persons to do the job | Optimal (O) | Normal (N) | Pess. (P) | Expected Time(Et) | Forecast Time Line
Scripts | David | 0.14 | 0.22 | 0.43 | 0.24167
Tool setup | David | 0.14 | 0.25 | 0.29 | 0.23833
Hiragana | David | 0.14 | 0.57 | 0.71 | 0.52167
Kanji | David | 0.14 | 0.22 | 0.29 | 0.21833
Survival Japanese | David | 1 | 2 | 3 | 2
Katakana | David | 0.14 | 0.57 | 0.71 | 0.52167
Culture: Social hierarchy and expressing respect in language | David | 0.14 | 0.2 | 0.29 | 0.205
Simple opinions | David | 0.14 | 0.29 | 0.71 | 0.335
Simple grammar: 2/wk | David | 0.14 | 0.24 | 0.36 | 0.24333
Small talk | David | 0.14 | 0.22 | 0.43 | 0.24167
Small expressions | David | 0.14 | 0.27 | 0.57 | 0.29833
Informed opinions (explanation) | David | 0.14 | 0.35 | 0.86 | 0.4
Culture | David | 1 | 1.7 | 2 | 1.6333
Vocabulary | David | 0.14 | 0.43 | 0.71 | 0.42833
Listening practice | David | 1 | 2 | 3.5 | 2.0833
Reading practice | David | 1 | 1.5 | 3 | 1.6667
Writing practice | David | 0.14 | 0.29 | 0.57 | 0.31167
Time line: weeks | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Total forecast expenditure |  | 5.26 | 10.06 | 16.71 | 10.3683 | 1: Forecasted end date:; 3: 14th September
Project Manager Signature / date | David Martin 3/07/2020 |  |  |  |  | 1: Senior Manager Signoff / date; 4: David Martin 3/07/2020
Just one simple sentence structure and some words